## Sheet1
Activity: Informix Migration to switch single Instance
DBA Contact: Sulochana Vemula |  | Application Contact: Sai Sachin Kumar
Task No | Task Name | Responsible | Duration(In Mins) | Comments
1 | Stop Application, CSM deamons and Tramo monitoring tools | APP Team | 40
2 | Stop the DBA monitoring and cron jobs in adetrmdb2 server | ADBA | 15
3 | DBA to take backup of production instances (rataktp1_vm,rataktp2_vm,rataktp4_vm,ratcalp2_vm) in adetrmdb2 server | ADBA | 20
4 | Transfer the data with scripts from rataktp2_vm,rataktp4_vm,ratcalp2_vm to rataktp1_vm server & Update statistics | ADBA | 90
5 | Start the un-buffered logging of databases on rataktp1_vm. | ADBA | 10
6 | Perform the Instance wise sanity and enable the DBA monitoring on adetrmdb2 | ADBA | 20
7 | Change Configuration of CSM60 Daemons on both albany6/7, hint /opt/informix/etc/sqlhosts & /ahaus(1/2)/var/oper/(mmc/mmo)/config/libtmack2k.env (root rights required) | APP Team | 10 | Deployment team is required
8 | Start the Daemons | APP Team | 20
9 | Check the connections for single Instance(rataktp1_vm) from CSM60 | ADBA | 5
10 | If task 10 successfully then only switch the configuration of erni and bert to single instance | APP Team | 10
11 | If task 10 is fails then to analyze/fallback | Analyze | 60
12 | Switch the Configuration and Start erni and bert (Only in rollback Situation) | APP Team | 15
13 | Switch the configuration of VAS on both adevas5/6s to single instance | APP Team | 20
14 | Switch the configuration and Create the SoftLink of d2as | APP Team | 15
15 | Check the connections for single Instance(rataktp1_vm) | ADBA | 5
16 | Place the test order and see it got successful (sanity/fallback) | APP Team | 60
17 | Switch the all monitoring tools(status monitor,blob reader,blob zahler,tramomonitor) to single Instances | APP Team | 45
18 | Adapt the configuration of OSCAR to single instance | APP Team | 10
19 | Check the connections of OSCAR in next day to validate the connection of single instance | APP Team | 10